## Procurement Plan
Quality and Cost Based Selection (QCBS), Fixed Budget Based Selection (FBBS), Least Cost Based Selection (LCBS)
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$)/INR | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expresson and Short List of consultant |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Opening of Financial Proposals / Minutes |  | Combined Evaluation Report and Negotiate Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
DGT-35-4-1-PMC STRIVE - 2016-NPIU / Hiring of Firm for providing Project Management Consultants (PMC) under the scheme STRIVE | IDA-59650 |  | Prior | Consultant Services | Open - National | USD3,660,552.69; INR 25,24,99,340 | Signed | Cleared | 2017-02-15 | 2017-07-20 | 2017-03-08 | 2017-07-24 | 2017-04-07 | 2017-07-25 | 2017-04-21 | 2017-07-26 |  |  |  | 2017-08-23 | 2017-08-07 | 2017-08-31 | 2017-08-28 | 2017-09-22 | 2017-09-18 | 2017-10-03 | 2017-10-23 | 2017-11-08 | 2017-11-06 | 2018-06-07 | 2017-11-27 | 2018-05-03 | 26/10/2020; 15/07/2021; 20/08/2021 | 2020-11-05 | 30/11/2022
IN-MSDE GOI-60479-CS- QCBS / Hiring of Consultancy Firm for conducting Gender Study under the Project STRIVE with World bank assistance. | IDA-59650 | Program Management Support for Strategic Technical Assistance for Improving Efficiency and Monitoring and Evaluation | Post | Consultant Services | Open - National | USD58,946/INR40,66,000 | Signed | Cleared | 2018-06-07 | 2018-06-12 | 2018-06-28 |  | 2018-07-28 | 2018-07-13 | 2018-08-11 | 2018-09-05 |  | 2018-09-05 |  | 2018-09-18 | 2018-09-08 | 2018-10-04 | 2018-10-08 | 2018-10-16 | 2018-10-22 | 2018-10-17 | 2018-11-12 |  | 2018-11-26 |  | 2018-12-17 | 21/01/2019 |  | 2019-12-18
DGT-35-4-DLI VERIFICATION- 2017-NPIU / Hiring of an "Independent Verification Agency" for the certification of Disbursement Linked Indicators (DLI) for 3 Years | IDA-59650 | Program Management Support for Strategic Technical Assistance for Improving Efficiency and Monitoring and Evaluation | Post | Consultant Services | Open - International | USD414,400/INR3,10,80,000 | Signed | Cleared | 2018-10-25 | 2018-11-16 | 2018-11-15 |  | 2018-12-15 |  | 2018-12-29 |  |  |  |  | Amendments no.DGT-35(4)/IVA-STRIVE/2018-NPIU (part) dated 30/06/2022 to extend the contract from 23/05/2022 to 30/11/2022 | 2019-01-26 |  | 2019-02-25 |  | 2019-03-11 |  | 2019-04-01 |  | 2019-04-15 |  | 5/6/2019 | 22/05/2020 & 23/05/2022 | Amendments no.DGT-35(4)/IVA-STRIVE/2018-NPIU (part) dated 30/06/2022 to extend the contract from 23/05/2022 to 30/11/2022 | 22/5/2020, Post amendment, last date of contract is 30/11/2022 | 22/5/2022 Post amendment, last date of contract is 30/11/2022