Program Action Plan (PAP) Update for period Jan – March 2022

This note provides a status on the procurement implementation activities undertaken by States/Union Territories (UTs) for the STRIVE Program. This premier edition captures summary of cumulative data reported by downstream implementing agencies (States and ITIs) till Q4 FY 2021-22 i.e., January 2022 – March 2022.  One of the key highlights of the report is that the implementing agencies have achieved the stated target of 60% in Year 4, as per Annex 8 of the Project Appraisal Document (PAD) of STRIVE. The achievement of PAP will be measured across PAP 1 and PAP 2. PAP 1 is further categorized into reporting from States and ITIs. The achievement status for period January 2022 – March 2022 is summarized below:

| Measurement Criteria | Number of implementing agencies funded by the project | PAP 1 |  |  | PAP 2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target [% and No.] | Status [% and No.] | Remarks | Target | Status | Remarks |
| No. of States (SPIUs and SAMCs) | 32* | 60% (19) | 69% (22) |  | Availability of functional procurement complaint handling and redressal mechanism on project website along with reports generated from the system | The same is available on DGT STRIVE microsite$ with No complaint received during the period from the IAs who reported the data. | Achieved |
| No. of ITIs | 425^ | 60% (255) | 90% (383) |  |  |  |  |
| No. of ICs | 33# | 60% (20) | 9% (3) |  |  |  |  |
| Total | 490 | 60% (294) | 83% (408) | Achieved |  |  |  |

*Total funded States/UTs are 34. However, no funds have been released to two UTs Chandigarh and Ladakh

^Total number of ITIs funded in the Program is 426, however 1 ITI of Chandigarh is not being considered due to lack of release of fund. Further, only 200 ITIs are earmarked to be directly funded by the World Bank as per DLI matrix.

# Industry Clusters were not in proposed plan of procurement monitoring for this quarter, but however, the team has proactively reached out to ICs selected under STRIVE and collected data from 2 ICs

$Link to the redressal mechanism: https://dgt.gov.in/sites/default/files/GuidanceNote-GRM.pdf

Annexure 1: Summary of PAP Compliance data

| S.No. | State/UT | Total Fund Release | State or UT | WB selected ITIs covered Yes/No | SPIU |  |  | Total no. of ITI's | No. of ITI for which data is reported | ITI-wise PAP compliance |  | Total no. of WB ITI's | No. of WB ITI's for which data is reported | WB ITIs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Data submitted | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 |
| 1 | Andhra Pradesh | 15.88 | State | Yes | Yes | Yes | Yes | 15 | 15 | Yes | Yes | 8 | 8 | Yes | Yes |
| 2 | Andaman and Nicobar Islands | 1.01 | UT | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 3 | Arunachal Pradesh | 2.96 | State | No | Yes | Yes | Yes | 1 | 0 | No | No | 0 | NA | NA | NA |
| 4 | Assam | 5.66 | State | Yes | Yes | Yes | Yes | 5 | 5 | Yes | Yes | 2 | 2 | Yes | Yes |
| 5 | Bihar | 4.64 | State | Yes | Yes | Yes | Yes | 4 | 4 | Yes | No | 3 | 3 | Yes | No |
| 6 | Chandigarh | 0 | UT | No | No | No | No | 0 | 0 | Yes | Yes | 0 | NA | NA | NA |
| 7 | Chhattisgarh | 13.18 | State | Yes | No | No | No | 17 | 13 | Yes | No | 4 | 2 | Yes | No |
| 8 | Delhi | 5.86 | UT | No | Yes | Yes | Yes | 4 | 1 | Yes | No | 0 | NA | NA | NA |
| 9 | Goa | 3.42 | State | No | No | No | No | 2 | 0 | No | No | 0 | NA | NA | NA |
| 10 | Gujarat | 30.75 | State | Yes | Yes | Yes | Yes | 40 | 38 | Yes | Yes | 14 | 14 | Yes | Yes |
| 11 | Haryana | 17.94 | State | Yes | Yes | Yes | Yes | 21 | 21 | Yes | Yes | 16 | 16 | Yes | Yes |
| 12 | Himachal Pradesh | 19.79 | State | Yes | Yes | Yes | Yes | 19 | 19 | Yes | Yes | 17 | 17 | Yes | Yes |
| 13 | Jammu and Kashmir | 7.00 | UT | No | Yes | Yes | Yes | 7 | 7 | Yes | Yes | 0 | NA | NA | NA |
| 14 | Jharkhand | 2.77 | State | No | Yes | Yes | Yes | 3 | 3 | No | No | 0 | NA | NA | NA |
| 15 | Karnataka | 20.39 | State | Yes | No | No | No | 22 | 20 | Yes | Yes | 19 | 17 | Yes | Yes |
| 16 | Kerala | 18.49 | State | Yes | No | No | No | 19 | 19 | Yes | Yes | 19 | 19 | Yes | Yes |
| 17 | Madhya Pradesh | 19.37 | State | No | No | No | No | 20 | 0 | No | No | 0 | NA | NA | NA |
| 18 | Maharashtra | 70.54 | State | Yes | Yes | Yes | Yes | 76 | 76 | Yes | No | 26 | 26 | Yes | Yes |
| 19 | Manipur | 1.92 | State | No | No | No | No | 1 | 1 | Yes | Yes | 0 | NA | NA | NA |
| 20 | Meghalaya | 1.83 | State | Yes | No | No | No | 1 | 0 | No | No | 1 | 0 | No | No |
| 21 | Mizoram | 2.10 | State | No | Yes | Yes | Yes | 1 | 0 | No | No | 0 | NA | NA | NA |
| 22 | Nagaland | 2.62 | State | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 23 | Odisha | 15.01 | State | Yes | Yes | Yes | Yes | 10 | 10 | NA | NA | 10 | 10 | Yes | Yes |
| 24 | Puducherry | 2.73 | UT | No | Yes | Yes | Yes | 2 | 0 | No | No | 0 | NA | NA | NA |
| 25 | Punjab | 19.80 | State | No | Yes | Yes | Yes | 24 | 24 | Yes | Yes | 0 | NA | NA | NA |
| 26 | Rajasthan | 15.72 | State | No | Yes | Yes | Yes | 14 | 13 | Yes | Yes | 0 | NA | NA | NA |
| 27 | Sikkim | 1.70 | State | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 28 | Tamil Nadu | 17.55 | State | Yes | Yes | Yes | Yes | 16 | 16 | Yes | Yes | 14 | 14 | Yes | Yes |
| 29 | Telangana | 10.03 | State | Yes | Yes | Yes | Yes | 10 | 10 | Yes | Yes | 9 | 9 | Yes | Yes |
| 30 | Tripura | 3.96 | State | Yes | Yes | Yes | Yes | 3 | 3 | Yes | Yes | 2 | 2 | Yes | Yes |
| 31 | Uttar Pradesh | 25.21 | State | Yes | Yes | Yes | Yes | 29 | 29 | Yes | Yes | 18 | 16 | Yes | Yes |
| 32 | Uttarakhand | 8.55 | State | Yes | Yes | Yes | Yes | 8 | 8 | Yes | Yes | 4 | 4 | Yes | Yes |
| 33 | West Bengal | 25.21 | State | Yes | Yes | Yes | Yes | 28 | 28 | Yes | Yes | 14 | 14 | Yes | Yes |
|  | Total |  |  |  | 22 |  |  | 425 | 383 |  |  | 200 | 193 |  |  |
| Note:1. States highlighted in red have not reported data at all, 2. NA denotes "Not Applicable" |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Further details of the data reported by States and ITIs can be accessed from the below link:

https://worldbankgroup-my.sharepoint.com/:u:/r/personal/kdatt_worldbank_org1/Documents/STRIVE%20Procurement/Q4%20FY%2022%20Data%20for%20the%20World%20Bank/Q4%20Jan%20to%20March%202022_V2%20Final.zip?csf=1&web=1&e=hxJlm6

PAP1 pertains to disclosure of procurement plans in standard formats by the implementing agencies of the project

PAP 2 pertains to disclosure and monitoring of procurement related grievances/complaints by implementing agencies of the project