Program Action Plan (PAP) Update for period October – December 2021

This note provides a status on the procurement implementation activities undertaken by States/Union Territories (UTs) for the STRIVE Program. This premier edition captures summary of cumulative data reported by downstream implementing agencies (States and ITIs) till Q3 FY 2021-22 i.e., October 2021 – December 2021.  One of the key highlights of the report is that the implementing agencies have achieved the stated target of 60% in Year 4, as per Annex 8 of the Project Appraisal Document (PAD) of STRIVE. The achievement of PAP will be measured across PAP 1 and PAP 2. PAP 1 is further categorized into reporting from States and ITIs. The achievement status for period October 2021 – December 2021 is summarized below:

| Measurement Criteria | Number of implementing agencies funded by the project | PAP 1 |  |  | PAP 2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target [% and No.] | Status [% and No.] | Remarks | Target | Status | Remarks |
| No. of States (SPIUs and SAMCs) | 32* | 60% (19) | 78% (25) |  | Availability of functional procurement complaint handling and redressal mechanism on project website along with reports generated from the system | The same is available on DGT STRIVE microsite$ with No complaint received during the period from the IAs who reported the data. | Achieved |
| No. of ITIs | 425^ | 60% (255) | 68% (288) |  |  |  |  |
| No. of ICs | 33# | 60% (20) | 18% (6) |  |  |  |  |
| Total | 490 | 60% (294) | 65% (319) | Achieved |  |  |  |

*Total funded States/UTs are 34. However, no funds have been released to two UTs Chandigarh and Ladakh. The same is attributed to the legislative structure of these UTs and hence are allowed only to be reimbursed for the expenses made by them.

^Total number of ITIs funded in the Program is 426. However, only 200 ITIs are earmarked to be directly funded by the World Bank as per DLI matrix.

# Industry Clusters were not in proposed plan of procurement monitoring for this quarter, but however, the team has proactively reached out to ICs selected under STRIVE and collected data from 6 ICs

$Link to the redressal mechanism: https://dgt.gov.in/sites/default/files/Advisory_E%26S_states_uts_.pdf

Annexure 1: Summary of PAP Compliance data

| S. No. | State/UT | PAP Data Shared with NPIU | Data of SPIU reported | SPIU Data/ PAP compliance |  | Total no. of ITI's in STRIVE | No. of ITI’s - Data reported | ITI-wise PAP compliance |  | No. of ITIs mapped for funding from the WB as per PAD | No. of WB funded ITI's who have reported the required Data | WB ITI-wise PAP compliance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 |  |  | PAP-1 | PAP-2 |
| 1 | Andhra Pradesh | Yes | Yes | Yes | Yes | 15 | 0 | No | No | 8 | 0 | No | No |
| 2 | Arunachal Pradesh | No | No | No | No | 1 | 0 | No | No | 0 | 0 | No | No |
| 3 | Assam | Yes | Yes | Yes | Yes | 5 | 5 | Yes | Yes | 2 | 2 | Yes | Yes |
| 4 | Bihar | Yes | Yes | Yes | Yes | 4 | 0 | No | No | 3 | 0 | No | No |
| 5 | Chhattisgarh | Yes | Yes | Yes | Yes | 17 | 15 | Yes | Yes | 4 | 3 | Yes | Yes |
| 6 | Gujarat | Yes | Yes | Yes | Yes | 40 | 38 | Yes | Yes | 14 | 14 | Yes | Yes |
| 7 | Haryana | Yes | Yes | Yes | Yes | 21 | 0 | No | No | 16 | 0 | No | No |
| 8 | Himachal Pradesh | Yes | Yes | Yes | Yes | 19 | 17 | Yes | Yes | 17 | 17 | Yes | Yes |
| 9 | Karnataka | Yes | Yes | Yes | No | 22 | 22 | Yes | Yes | 19 | 19 | Yes | Yes |
| 10 | Kerala | Yes | No | No | No | 19 | 2 | Yes | Yes | 19 | 2 | Yes | Yes |
| 11 | Maharashtra | Yes | Yes | Yes | Yes | 76 | 76 | Yes | No | 26 | 26 | Yes | No |
| 12 | Meghalaya | Yes | Yes | Yes | Yes | 1 | 1 | Yes | Yes | 1 | 1 | Yes | Yes |
| 13 | Odisha | Yes | No | No | No | 10 | 10 | Yes | Yes | 10 | 10 | Yes | Yes |
| 14 | Tamil Nadu | Yes | Yes | Yes | Yes | 16 | 16 | Yes | Yes | 14 | 14 | Yes | Yes |
| 15 | Telangana | Yes | No | No | No | 10 | 0 | No | No | 9 | 0 | No | No |
| 16 | Tripura | Yes | Yes | Yes | Yes | 3 | 3 | Yes | Yes | 2 | 2 | Yes | Yes |
| 17 | Uttar Pradesh | Yes | Yes | Yes | Yes | 29 | 14 | Yes | Yes | 18 | 13 | Yes | Yes |
| 18 | Uttarakhand | Yes | Yes | Yes | Yes | 8 | 8 | Yes | Yes | 4 | 4 | Yes | Yes |
| 19 | West Bengal | Yes | Yes | Yes | Yes | 28 | 28 | Yes | Yes | 14 | 14 | Yes | Yes |
| 20 | Sikkim | Yes | Yes | Yes | Yes | 1 | 0 | No | No | 0 | NA | NA | NA |
| 21 | Rajasthan | No | No | No | No | 14 | 0 | No | No | 0 | NA | NA | NA |
| 22 | Jharkhand | No | No | No | No | 3 | 0 | No | No | 0 | NA | NA | NA |
| 23 | Madhya Pradesh | No | No | No | No | 20 | 0 | No | No | 0 | NA | NA | NA |
| 24 | Manipur | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 25 | Mizoram | Yes | Yes | Yes | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 26 | Nagaland | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 27 | Punjab | Yes | Yes | Yes | Yes | 24 | 24 | Yes | Yes | 0 | NA | NA | NA |
| 28 | Goa | Yes | Yes | Yes | Yes | 2 | 2 | Yes | Yes | 0 | NA | NA | NA |
| 29 | Puducherry | Yes | Yes | Yes | Yes | 2 | 0 | No | No | 0 | NA | NA | NA |
| 30 | Andaman and Nicobar Islands | No | No | No | No | 1 | 0 | No | No | 0 | NA | NA | NA |
| 31 | Delhi | Yes | Yes | Yes | Yes | 4 | 0 | No | No | 0 | NA | NA | NA |
| 32 | Jammu and Kashmir | Yes | Yes | Yes | Yes | 7 | 7 | Yes | Yes | 0 | NA | NA | NA |
|  | Total |  |  |  |  | 425 | 288 |  |  | 200 | 141 |  |  |

Further details of the data reported by States and ITIs can be accessed from the below link:

https://drive.google.com/drive/folders/1rX1zmrf0elgGBQHmkCKYxZbSx-Po1MXU?usp=sharing

PAP1 pertains to disclosure of procurement plans in standard formats by the implementing agencies of the project

PAP 2 pertains to disclosure and monitoring of procurement related grievances/complaints by implementing agencies of the project

One complaint has been registered on integrated GRM portal. The same is under resolution with West Bengal SPIU and the status of resolution will be provided in next report. The detail of the complaint, as generated from the system, is shared separately via email.